## 00_README
CHINAIMO — SCHEDULE LOGIC / MONTHLY PROGRESS / S-CURVE ANNEX
Separate reviewer annex so the final beautified Master Excel remains lean and unchanged.
CONTROL ITEM | LOCKED VALUE / RULE
Assessment baseline start | 2025-10-01
Native baseline finish | 2028-02-15
Assessment data date | 2026-08-31
Native current forecast | 2028-06-23
Native partial recovery | 2028-04-14
Public completion target | July 2028 (separate public target reference)
Progress basis | 4.19% public checkpoint @ 05-May-2026; 12.095% assessment-simulated @ 31-Aug-2026
LOGIC NOTATION | MEANING
FS | Finish-to-Start
SS | Start-to-Start
SS+5d | Start-to-Start with 5 working-day lag
Multiple predecessors | Semicolon-separated predecessor IDs and relationship strings pair in the same order.
Boundary | Logic and durations are assessment-derived for demonstration; they are not represented as Kubota's confidential approved programme.
S-CURVE NOTE — Baseline Planned % is the assessment control curve. The two future curves are illustrative smooth interpolations anchored to the native Microsoft Project completion dates (23-Jun-2028 current and 14-Apr-2028 recovery). They demonstrate forecast presentation only and are not contractual cash-flow, earned-value, manpower, or Kubota internal curves.

## 01_SCHEDULE_LOGIC
ASSESSMENT BASELINE — ACTIVITY LOGIC & PREDECESSOR RELATIONSHIPS
Same Activity IDs and dependency logic used to build the native Microsoft Project baseline. Baseline dates are reconciled to the final 01-Oct-2025 start / 15-Feb-2028 finish.
Activity ID | WBS | Workstream | Activity Name | Duration (wd) | Predecessor ID(s) | Relationship(s) | Readable Logic | Baseline Start | Baseline Finish | Total Slack (wd) | Critical?
PREL-010 | 1.1 | Preliminaries | Notice to Proceed | 0 |  |  | — | 2025-10-01 | 2025-10-01 | 0 | YES
PREL-020 | 1.2 | Preliminaries | Mobilization & Temporary Facilities | 20 | PREL-010 | FS | PREL-010 (FS) | 2025-10-01 | 2025-10-23 | 0 | YES
PREL-030 | 1.3 | Preliminaries | Survey / Setting Out | 15 | PREL-020 | SS+5d | PREL-020 (SS+5d) | 2025-10-07 | 2025-10-23 | 0 | YES
DES-010 | 2.1 | Design & Procurement | Review IFC Drawings / Interfaces | 30 | PREL-010 | FS | PREL-010 (FS) | 2025-10-01 | 2025-11-04 | 64 | NO
DES-020 | 2.2 | Design & Procurement | Method Statements & Material Submittals | 45 | DES-010 | SS+10d | DES-010 (SS+10d) | 2025-10-13 | 2025-12-03 | 64 | NO
PROC-010 | 2.3 | Design & Procurement | Long-Lead M&E Procurement | 300 | DES-020 | FS | DES-020 (FS) | 2025-12-04 | 2026-11-18 | 64 | NO
PROC-020 | 2.4 | Design & Procurement | SCADA / Instrumentation Procurement | 260 | DES-020 | FS | DES-020 (FS) | 2025-12-04 | 2026-10-02 | 204 | NO
PROC-030 | 2.5 | Design & Procurement | Electrical / Receiving Equipment Procurement | 240 | DES-020 | FS | DES-020 (FS) | 2025-12-04 | 2026-09-09 | 124 | NO
WTP-CIV-010 | 3.1 | Chinaimo WTP | Site Clearing / Excavation / Dewatering | 35 | PREL-030 | FS | PREL-030 (FS) | 2025-10-24 | 2025-12-03 | 0 | YES
WTP-CIV-020 | 3.2 | Chinaimo WTP | Ground Preparation / Blinding | 15 | WTP-CIV-010 | FS | WTP-CIV-010 (FS) | 2025-12-04 | 2025-12-20 | 0 | YES
WTP-CIV-030 | 3.3 | Chinaimo WTP | WTP Foundations / Base Slabs | 60 | WTP-CIV-020 | FS | WTP-CIV-020 (FS) | 2025-12-22 | 2026-02-28 | 0 | YES
WTP-CIV-040 | 3.4 | Chinaimo WTP | Mixing / Flocculation Basin RC Works | 70 | WTP-CIV-030 | FS | WTP-CIV-030 (FS) | 2026-03-02 | 2026-05-21 | 0 | YES
WTP-CIV-050 | 3.5 | Chinaimo WTP | Sedimentation Basin RC Works | 100 | WTP-CIV-040 | SS+20d | WTP-CIV-040 (SS+20d) | 2026-03-25 | 2026-07-18 | 0 | YES
WTP-CIV-060 | 3.6 | Chinaimo WTP | Rapid Sand Filter Structure | 80 | WTP-CIV-050 | FS | WTP-CIV-050 (FS) | 2026-07-20 | 2026-10-20 | 0 | YES
WTP-CIV-070 | 3.7 | Chinaimo WTP | Internal Channels / Pipe Galleries | 45 | WTP-CIV-060 | FS | WTP-CIV-060 (FS) | 2026-10-21 | 2026-12-11 | 0 | YES
WTP-CIV-080 | 3.8 | Chinaimo WTP | Waterproofing / Protective Coating | 30 | WTP-CIV-070 | FS | WTP-CIV-070 (FS) | 2026-12-12 | 2027-01-15 | 0 | YES
WTP-CIV-090 | 3.9 | Chinaimo WTP | Hydrostatic / Structural Water Test | 14 | WTP-CIV-080 | FS | WTP-CIV-080 (FS) | 2027-01-16 | 2027-02-01 | 0 | YES
RES-010 | 4.1 | Chinaimo Reservoir | 10,000 m³ Reservoir Excavation | 40 | PREL-030 | FS | PREL-030 (FS) | 2025-10-24 | 2025-12-09 | 330 | NO
RES-020 | 4.2 | Chinaimo Reservoir | Reservoir Foundation / Base Slab | 60 | RES-010 | FS | RES-010 (FS) | 2025-12-10 | 2026-02-17 | 330 | NO
RES-030 | 4.3 | Chinaimo Reservoir | Reservoir Walls / Columns | 100 | RES-020 | FS | RES-020 (FS) | 2026-02-18 | 2026-06-13 | 330 | NO
RES-040 | 4.4 | Chinaimo Reservoir | Reservoir Roof Slab | 60 | RES-030 | FS | RES-030 (FS) | 2026-06-15 | 2026-08-22 | 330 | NO
RES-050 | 4.5 | Chinaimo Reservoir | Reservoir Waterproofing / Coating | 30 | RES-040 | FS | RES-040 (FS) | 2026-08-24 | 2026-09-26 | 330 | NO
RES-060 | 4.6 | Chinaimo Reservoir | Reservoir Hydrostatic Test | 14 | RES-050 | FS | RES-050 (FS) | 2026-09-28 | 2026-10-13 | 330 | NO
BLDG-010 | 5.1 | Buildings | Pump Room Civil / Structural Works | 75 | WTP-CIV-030 | SS+20d | WTP-CIV-030 (SS+20d) | 2026-01-14 | 2026-04-10 | 254 | NO
BLDG-020 | 5.2 | Buildings | Chemical Building Civil / Architectural | 90 | WTP-CIV-030 | SS+30d | WTP-CIV-030 (SS+30d) | 2026-01-26 | 2026-05-09 | 349 | NO
BLDG-030 | 5.3 | Buildings | Administration & Laboratory Building | 120 | WTP-CIV-010 | FS | WTP-CIV-010 (FS) | 2025-12-04 | 2026-04-22 | 499 | NO
BLDG-040 | 5.4 | Buildings | Building MEP / Architectural Finishes | 70 | BLDG-030 | FS | BLDG-030 (FS) | 2026-04-23 | 2026-07-13 | 499 | NO
ME-010 | 6.1 | Process M&E | Process Piping Installation | 100 | WTP-CIV-090;PROC-010 | FS;FS | WTP-CIV-090 (FS); PROC-010 (FS) | 2027-02-02 | 2027-05-28 | 0 | YES
ME-020 | 6.2 | Process M&E | Pumps & Mechanical Equipment Installation | 90 | BLDG-010;PROC-010 | FS;FS | BLDG-010 (FS); PROC-010 (FS) | 2026-11-19 | 2027-03-03 | 164 | NO
ME-030 | 6.3 | Process M&E | Chemical Dosing Equipment Installation | 70 | BLDG-020;PROC-010 | FS;FS | BLDG-020 (FS); PROC-010 (FS) | 2026-11-19 | 2027-02-08 | 184 | NO
ME-040 | 6.4 | Process M&E | Filter Media / Underdrain Equipment | 50 | WTP-CIV-090;PROC-010 | FS;FS | WTP-CIV-090 (FS); PROC-010 (FS) | 2027-02-02 | 2027-03-31 | 140 | NO
ME-050 | 6.5 | Process M&E | Electrical Installation / MCC / Cabling | 100 | BLDG-010;PROC-030 | FS;FS | BLDG-010 (FS); PROC-030 (FS) | 2026-09-10 | 2027-01-04 | 124 | NO
ME-060 | 6.6 | Process M&E | Instrumentation & SCADA Installation | 90 | ME-010;ME-050;PROC-020 | FS;FS;FS | ME-010 (FS); ME-050 (FS); PROC-020 (FS) | 2027-05-29 | 2027-09-10 | 0 | YES
SAL-010 | 7.1 | Salakham | Salakham Site Preparation / Excavation | 40 | PREL-030 | FS | PREL-030 (FS) | 2025-10-24 | 2025-12-09 | 334 | NO
SAL-020 | 7.2 | Salakham | 7,100 m³ Reservoir RC Works | 180 | SAL-010 | FS | SAL-010 (FS) | 2025-12-10 | 2026-07-07 | 334 | NO
SAL-030 | 7.3 | Salakham | Salakham Pump Room | 90 | SAL-010 | SS+30d | SAL-010 (SS+30d) | 2025-11-28 | 2026-03-12 | 434 | NO
SAL-040 | 7.4 | Salakham | Salakham M&E Installation | 80 | SAL-020;SAL-030;PROC-010 | FS;FS;FS | SAL-020 (FS); SAL-030 (FS); PROC-010 (FS) | 2026-11-19 | 2027-02-19 | 219 | NO
PWR-010 | 8.1 | Power | 22-kV Route Survey / Permits | 45 | PREL-020 | FS | PREL-020 (FS) | 2025-10-24 | 2025-12-15 | 294 | NO
PWR-020 | 8.2 | Power | Pole / Foundation Works | 100 | PWR-010 | FS | PWR-010 (FS) | 2025-12-16 | 2026-04-10 | 294 | NO
PWR-030 | 8.3 | Power | 22-kV Line Installation | 120 | PWR-020 | FS | PWR-020 (FS) | 2026-04-11 | 2026-08-28 | 294 | NO
PWR-040 | 8.4 | Power | Receiving Equipment / Energization | 30 | PWR-030;PROC-030 | FS;FS | PWR-030 (FS); PROC-030 (FS) | 2026-09-10 | 2026-10-14 | 284 | NO
COMM-010 | 9.1 | Commissioning | Mechanical Pre-Commissioning | 25 | ME-010;ME-020;ME-030;ME-040 | FS;FS;FS;FS | ME-010 (FS); ME-020 (FS); ME-030 (FS); ME-040 (FS) | 2027-05-29 | 2027-06-26 | 90 | NO
COMM-020 | 9.2 | Commissioning | Electrical / I&C Pre-Commissioning | 25 | ME-060;PWR-040 | FS;FS | ME-060 (FS); PWR-040 (FS) | 2027-09-11 | 2027-10-09 | 0 | YES
COMM-030 | 9.3 | Commissioning | Dry Commissioning | 20 | COMM-010;COMM-020 | FS;FS | COMM-010 (FS); COMM-020 (FS) | 2027-10-11 | 2027-11-02 | 0 | YES
COMM-040 | 9.4 | Commissioning | Wet Commissioning / Process Start-Up | 30 | COMM-030;RES-060;SAL-040 | FS;FS;FS | COMM-030 (FS); RES-060 (FS); SAL-040 (FS) | 2027-11-03 | 2027-12-07 | 0 | YES
COMM-050 | 9.5 | Commissioning | Performance / Water Quality Testing | 30 | COMM-040 | FS | COMM-040 (FS) | 2027-12-08 | 2028-01-11 | 0 | YES
COMM-060 | 9.6 | Commissioning | Punch List / Rectification | 30 | COMM-050 | FS | COMM-050 (FS) | 2028-01-12 | 2028-02-15 | 0 | YES
COMM-070 | 9.7 | Commissioning | Training / O&M Documents | 20 | COMM-040 | SS | COMM-040 (SS) | 2027-11-03 | 2027-11-25 | 70 | NO
COMM-080 | 9.8 | Commissioning | Taking Over / Completion Milestone | 0 | COMM-060;COMM-070;BLDG-040 | FS;FS;FS | COMM-060 (FS); COMM-070 (FS); BLDG-040 (FS) | 2028-02-15 | 2028-02-15 | 0 | YES

## 02_MONTHLY_S_CURVE
MONTHLY PROGRESS REGISTER & S-CURVE | [7 empty] | CONTROL | VALUE
Public / assessment status points are shown only where evidence exists. No invented monthly actuals are backfilled. | [7 empty] | Status date | 2026-08-31
[8 empty] | Assessment progress | 12.1%
Period End | Baseline Planned Cum. % | Baseline Monthly % | Reported / Assessment Cum. % | Variance vs Plan (pp) | Current Forecast Curve % | Recovery Curve % | Basis / Note | Baseline finish | 2028-02-15 | Chart Month
2025-10-31 | 1% | 1% | [5 empty] | Current forecast finish | 2028-06-23 | Oct-25
2025-11-30 | 2.5% | 1.5% | [5 empty] | Recovery finish | 2028-04-14 | Nov-25
2025-12-31 | 4.5% | 2% | [5 empty] | Public checkpoint | 4.19% | Dec-25
2026-01-31 | 7% | 2.5% | [5 empty] | Public checkpoint date | 2026-05-05 | Jan-26
2026-02-28 | 10% | 3% | [5 empty] | Chart shows assessment Baseline / Current Forecast / Recovery curves only. Reported / assessment progress remains as exact points in the table to avoid inventing monthly actuals. |  | Feb-26
2026-03-31 | 14% | 4% | [7 empty] | Mar-26
2026-04-30 | 18% | 4% | [7 empty] | Apr-26
2026-05-31 | 23% | 5% | 4.19% | -18.81% |  |  | PUBLIC: 4.19% overall progress checkpoint at 05-May-2026. |  |  | May-26
2026-06-30 | 29% | 6% | [7 empty] | Jun-26
2026-07-31 | 35% | 6% | [7 empty] | Jul-26
2026-08-31 | 41% | 6% | 12.1% | -28.9% | 12.1% | 12.1% | ASSESSMENT: 12.095% simulated status at 31-Aug-2026; not a claimed Kubota actual. |  |  | Aug-26
2026-09-30 | 47% | 6% |  |  | 12.62% | 12.75% |  |  |  | Sep-26
2026-10-31 | 53% | 6% |  |  | 14.2% | 14.7% |  |  |  | Oct-26
2026-11-30 | 59% | 6% |  |  | 16.62% | 17.69% |  |  |  | Nov-26
2026-12-31 | 65% | 6% |  |  | 19.95% | 21.76% |  |  |  | Dec-26
2027-01-31 | 71% | 6% |  |  | 24.01% | 26.67% |  |  |  | Jan-27
2027-02-28 | 76% | 5% |  |  | 28.22% | 31.72% |  |  |  | Feb-27
2027-03-31 | 81% | 5% |  |  | 33.37% | 37.84% |  |  |  | Mar-27
2027-04-30 | 86% | 5% |  |  | 38.75% | 44.15% |  |  |  | Apr-27
2027-05-31 | 90% | 4% |  |  | 44.61% | 50.93% |  |  |  | May-27
2027-06-30 | 93% | 3% |  |  | 50.48% | 57.61% |  |  |  | Jun-27
2027-07-31 | 95% | 2% |  |  | 56.65% | 64.46% |  |  |  | Jul-27
2027-08-31 | 97% | 2% |  |  | 62.8% | 71.14% |  |  |  | Aug-27
2027-09-30 | 98.5% | 1.5% |  |  | 68.64% | 77.28% |  |  |  | Sep-27
2027-10-31 | 99.3% | 0.8% |  |  | 74.45% | 83.14% |  |  |  | Oct-27
2027-11-30 | 99.7% | 0.4% |  |  | 79.76% | 88.21% |  |  |  | Nov-27
2027-12-31 | 100% | 0.3% |  |  | 84.82% | 92.68% |  |  |  | Dec-27
2028-01-31 | 100% | 0% |  |  | 89.33% | 96.22% |  |  |  | Jan-28
2028-02-29 | 100% | 0% |  |  | 92.96% | 98.55% |  |  |  | Feb-28
Boundary: the baseline curve and predecessor logic are assessment-derived demonstration controls. Only 4.19% @ 05-May-2026 is a public overall progress checkpoint; 12.095% @ 31-Aug-2026 is explicitly simulated. Native Microsoft Project governs the schedule finish dates.