# CHINAIMO PROJECT CONTROLS RECOVERY ASSESSMENT

Reviewer Companion — Baseline, Actual Progress, Recovery & Sample IPC

Prepared by Michael Futol · Data date for assessment simulation: 31-Aug-2026

Purpose. Provide a concise, auditable explanation of the master Excel workbook and exactly three native Microsoft Project models. Public project facts are used only as anchors; all detailed task status, BOQ allocation and recovery actions are transparently assessment-derived.

# 1. CONTROL BASIS AND DATA BOUNDARY

| CONTROL ITEM | VALUE | TREATMENT |
| --- | --- | --- |
| Public construction start | October 2025 | 01-Oct-2025 used as a modeling convention because the public record gives a month, not the exact contractual NTP day. |
| Published implementation period | 30 months | Public anchor. |
| Public progress checkpoint | 4.19% at 05-May-2026 | Public fact; not extrapolated as if it were a live Kubota report. |
| Assessment data date | 31-Aug-2026 | BOQ/value-weighted progress simulated at 12.095%. |
| Latest public completion target | July 2028 | Public target reference only; the native Microsoft Project current forecast is 23-Jun-2028 and is not forced to the July target. |
| Public package value | JPY 6,478,257,873 | Public record. |
| Assessment control value | JPY 6,000,000,000 | Illustrative BOQ/control budget; not Kubota contract BOQ. |

# 2. THREE-MODEL SCHEDULE GOVERNANCE

The submission is deliberately reduced to the minimum live-control chain: Baseline → Actual Progress → Recovery.

| MODEL | ANCHOR / DATA DATE | FORECAST FINISH | DIFFERENCE | PURPOSE |
| --- | --- | --- | --- | --- |
| 1 · Baseline | 01-Oct-2025 | 15-Feb-2028 | 0 wd | Preserved Rev 0 reference. |
| 2 · Actual Progress / Current Forecast | 31-Aug-2026 | 23-Jun-2028 | +111 wd | Statused forecast; task actuals simulated. |
| 3 · Partial Recovery | 31-Aug-2026 | 14-Apr-2028 | 60 wd recovered / 51 wd residual | Partial recovery; field validate. |

Key rule: the Original Assessment Baseline (Rev 0) remains pristine. Monthly updates never overwrite it. A revised baseline is created only after a formally approved change when rebaselining is actually required.

# 3. STATUSING AND PROGRESS METHOD

The public record gives only one Chinaimo-specific overall checkpoint used here: 4.19% at 05-May-2026. Because the assessment is being submitted on 31-Aug-2026, the workbook uses a clearly labeled assessment simulation of 12.095% BOQ/value-weighted progress. The task-level percentages in Microsoft Project are schedule-status assumptions, not claims of Kubota internal actuals and not necessarily equal to BOQ-weighted earned progress.

Incomplete work that would otherwise remain in the past is moved to the assessment status date before recalculating the forecast. This preserves a clean data-date discipline: completed work stays in history; unfinished work is forecast from the status date forward.

# 4. BASELINE, VARIATIONS AND REVISED BASELINES

| CONTROL ITEM | VALUE | TREATMENT |
| --- | --- | --- |
| Original Assessment Baseline — Rev 0 | Frozen | Preserve the original approved/assessment reference and never rewrite history. |
| Monthly / periodic update | Working status model | Update actual starts/finishes, % complete, remaining duration, logic where properly authorized, and current forecast. |
| Pending variation / EOT | Forecast/change register | Assess effect without changing the baseline until contractual approval. |
| Approved variation with no time effect | Keep baseline finish | Update scope/cost records; do not rebaseline merely because value changed. |
| Approved time-changing variation / EOT | Approved Revised Baseline — Rev n | Create a new controlled baseline with approval reference/effective date while retaining Rev 0. |

# 5. MONTHLY REPORTING AND SAMPLE INTERIM PAYMENT CERTIFICATE

Monthly reporting is used as the assessment convention because it is a standard project-controls cycle and is consistent with JICA standard Works provisions for monthly Statements and interim payment certification. The exact CP-1 cut-off date, retention, advance recovery, taxes, currencies and minimum certificate amount are not assumed where the Particular Conditions are not publicly available.

| SAMPLE IPC LINE | ASSESSMENT VALUE | BOUNDARY / NOTE |
| --- | --- | --- |
| Assessment control value | JPY 6,000,000,000 | Illustrative control budget; not the Kubota contract BOQ. |
| Previous certified / earned progress | 9.50% | Assessment assumption for sample IPC only. |
| Current-period progress | 2.595% | Derived so cumulative assessment progress reaches 12.095%. |
| Cumulative assessment progress | 12.095% | BOQ/value-weighted assessment simulation at 31-Aug-2026. |
| Current gross work value | JPY 155,700,000 | Illustrative monthly valuation. |
| Retention | 10% = JPY 15,570,000 | Illustrative assumption; actual percentage comes from Contract Data / Particular Conditions. |
| Advance recovery / other deductions | Nil in sample | Not assumed without contract data. |
| Sample net current IPC | JPY 140,130,000 | Demonstration only; not a real Kubota payment certificate. |

# 6. REVIEWER FAQ

## WHY IS THE CURRENT ASSESSMENT PROGRESS 12.095% WHEN THE PUBLIC RECORD SAYS 4.19%?

4.19% is the dated public fact at 05-May-2026. 12.095% is a clearly labeled assessment simulation at 31-Aug-2026, used so the submission does not freeze the project four months in the past. It is not Kubota-reported progress.

## WHY NOT CREATE MANY DELAY SCENARIO MPP FILES?

Normal schedule governance only needs the preserved baseline, a statused current forecast and a recovery programme. Delay-analysis principles can be explained without multiplying native schedules.

## DOES +111 WORKING DAYS MEAN KUBOTA IS CONTRACTUALLY 111 DAYS IN DELAY?

No. It is a forecast difference between assessment states. Contractual delay, EOT, concurrency, responsibility and entitlement require the actual contract, accepted programme, notices and contemporaneous causation records.

## WHY IS RECOVERY ONLY PARTIAL?

A credible plan should not erase delay by assumption. The test recovers 60 working days and leaves 51 working days visible; every action remains subject to constructability, procurement, QA/QC, HSE, commercial and resource validation.

## WHAT IS THE BASELINE CRITICAL PATH?

The preserved baseline controls through commencement/mobilization and survey, the principal WTP civil sequence, process piping, instrumentation/SCADA and commissioning/closeout to completion. Current and recovery critical paths must be read from their own native MPPs because status can change the controlling path.

## WHY CAN BOQ PROGRESS DIFFER FROM MICROSOFT PROJECT % COMPLETE?

They measure different things: BOQ progress represents earned quantity/value, while task % Complete is used for schedule status and remaining-work placement. They should reconcile logically, not be forced to match numerically.

## HOW WOULD YOU HANDLE REAL PROJECT DATA IF HIRED?

Replace assessment assumptions with the accepted programme, actual cut-offs, measured quantities, procurement status, approved changes, productivity evidence and commercial terms, while preserving a reproducible update audit trail.

# 7. PUBLIC SOURCE BASIS

KPL — KUBOTA AGREEMENT / OCTOBER 2025 START / 30-MONTH IMPLEMENTATION: https://kpl.gov.la/en/detail.aspx?id=94243

VIENTIANE TIMES — PACKAGE VALUE / IMPLEMENTATION PERIOD: https://vientianetimes.org.la/freefreenews/freecontent_159_city_y25.php

KPL — GROUNDBREAKING / 2028 COMPLETION CONTEXT: 
https://kpl.gov.la/en/detail.aspx?id=94793

VIENTIANE TIMES — 4.19% ON 05-MAY-2026 / JULY-2028 COMPLETION TARGET: https://www.vientianetimes.org.la/freefreenews/freecontent_82_City_y26.php

JICA STANDARD BIDDING DOCUMENTS — MONTHLY STATEMENTS / INTERIM PAYMENT FRAMEWORK: https://www.jica.go.jp/activities/schemes/finance_co/procedure/guideline/tender/ku57pq00000v0qfy-att/SBDW_GC.pdf