## 00_SUMMARY
MICHAEL FUTOL — CHINAIMO PROJECT CONTROLS ASSESSMENT
Lean reviewer workbook. Public facts are separated from assessment simulation. Data date for the simulated current status: 31-Aug-2026.
PUBLIC ANCHOR | VALUE | BASIS | CURRENT ASSESSMENT | VALUE | BASIS | MODEL | FORECAST
Construction start | Oct-2025 | Public | Simulated current progress | 12.1% | Assessment only | Baseline | 2028-02-15
Implementation period | 30 months | Public | Status / Data Date | 2026-08-31 | Assessment date | Actual Progress | 2028-06-23
Public progress checkpoint | 4.19% | 05-May-2026 | Latest public % found | 4.19% | No newer public project % found | Recovery | 2028-04-14
Public current completion target | July 2028 | Public | Simulated current progress | 12.1% | Derived from 02_STATUS | Recovery gain vs current | 60 wd
Public package value | ¥6,478,257,873 | Public report | Model boundary | Public facts + simulation | No confidential Kubota data | Residual vs baseline | 51 wd
ONE SENTENCE TO DEFEND THE MODEL
The only published overall progress percentage used as fact is 4.19% at 05-May-2026; the 31-Aug-2026 status is a transparent assessment simulation (12.10%) built only to demonstrate how I would update, forecast and recover a live programme.
BASELINE CONTROL
Original Contract Baseline (Rev 0) | FROZEN / PRISTINE | Original approved reference is retained unchanged for full traceability.
Approved Revised Baseline (Rev n) | FORMAL APPROVAL ONLY | Create only after approved Variation/EOT/authorized change, with approval reference and effective date.
Monthly Working Update | EACH REPORTING PERIOD | Update actuals and remaining forecast monthly; do not redefine or overwrite the approved baseline.
Control Rule | KEEP REV 0 | Even after an approved rebaseline, keep the original contract baseline available and identifiable.
SAMPLE IPC — 31-Aug-2026: monthly assessment certificate included in 06_IPC_SAMPLE; commercial terms remain illustrative unless supported by CP-1 Particular Conditions.
MODEL BOUNDARY — Do not present simulated task actuals, quantities, rates, delay entitlement, payment terms or recovery commitments as Kubota records.

## 01_BOQ
ASSESSMENT BOQ / CONTROL BUDGET
Illustrative quantities and rates for method demonstration only. They are not Kubota's contract BOQ.
BOQ ID | Work Package | Unit | Qty | Rate (JPY) | Control Amount (JPY) | Weight % | Boundary
PREL-001 | Preliminaries / Temporary Works | LS | 1 | 300000000 | 300000000 | 5% | Assessment
CIV-001 | Earthworks / Excavation / Dewatering | m³ | 185000 | 2000 | 370000000 | 6.167% | Assessment
RC-001 | Structural Concrete | m³ | 45000 | 30000 | 1350000000 | 22.5% | Assessment
RB-001 | Reinforcement Steel | t | 7500 | 120000 | 900000000 | 15% | Assessment
FW-001 | Formwork | m² | 170000 | 2000 | 340000000 | 5.667% | Assessment
WPF-001 | Waterproofing / Protective Coating | m² | 85000 | 2000 | 170000000 | 2.833% | Assessment
MECH-001 | Process Piping / Mechanical | LS | 1 | 550000000 | 550000000 | 9.167% | Assessment
PMP-001 | Pumps / Major Mechanical Equipment | LS | 1 | 500000000 | 500000000 | 8.333% | Assessment
CHEM-001 | Chemical Dosing Systems | LS | 1 | 240000000 | 240000000 | 4% | Assessment
ELEC-001 | Electrical / MCC / Cabling | LS | 1 | 420000000 | 420000000 | 7% | Assessment
SCADA-001 | Instrumentation / SCADA | LS | 1 | 270000000 | 270000000 | 4.5% | Assessment
PWR-001 | 22-kV Off-site Power Works | LS | 1 | 240000000 | 240000000 | 4% | Assessment
BLDG-001 | Administration / Lab / Support Buildings | LS | 1 | 240000000 | 240000000 | 4% | Assessment
COMM-001 | Testing / Commissioning / Handover | LS | 1 | 110000000 | 110000000 | 1.833% | Assessment
TOTAL |  |  |  |  | 6000000000 | 100% | CHECK

## 02_STATUS
PROGRESS STATUS — PUBLIC CHECKPOINT → SIMULATED CURRENT STATUS
05-May-2026 overall progress (4.19%) is public. Item-level allocations in both columns are assessment reconstructions; 31-Aug-2026 is a conservative simulated update, not a claimed actual Kubota record.
BOQ ID | Work Package | Weight % | 05-May-2026 Allocation % | 31-Aug-2026 Simulated % | Earned Weight @ May | Earned Weight @ Aug
PREL-001 | Preliminaries / Temporary Works | 5% | 26.43% | 52% | 1.322% | 2.6%
CIV-001 | Earthworks / Excavation / Dewatering | 6.167% | 15% | 46% | 0.925% | 2.837%
RC-001 | Structural Concrete | 22.5% | 5% | 15% | 1.125% | 3.375%
RB-001 | Reinforcement Steel | 15% | 1.5% | 10% | 0.225% | 1.5%
FW-001 | Formwork | 5.667% | 2% | 11% | 0.1133% | 0.6233%
WPF-001 | Waterproofing / Protective Coating | 2.833% | 0% | 0% | 0% | 0%
MECH-001 | Process Piping / Mechanical | 9.167% | 0% | 0% | 0% | 0%
PMP-001 | Pumps / Major Mechanical Equipment | 8.333% | 0% | 0% | 0% | 0%
CHEM-001 | Chemical Dosing Systems | 4% | 0% | 0% | 0% | 0%
ELEC-001 | Electrical / MCC / Cabling | 7% | 0% | 0% | 0% | 0%
SCADA-001 | Instrumentation / SCADA | 4.5% | 0% | 0% | 0% | 0%
PWR-001 | 22-kV Off-site Power Works | 4% | 2% | 7% | 0.08% | 0.28%
BLDG-001 | Administration / Lab / Support Buildings | 4% | 10% | 22% | 0.4% | 0.88%
COMM-001 | Testing / Commissioning / Handover | 1.833% | 0% | 0% | 0% | 0%
TOTAL WEIGHTED PROJECT PROGRESS |  | 100% |  |  | 4.19% | 12.1%
Assessment rationale for 12.10%: four months after the 4.19% public checkpoint, the simulation assumes continued early-civil ramp-up (earthworks, concrete, rebar/formwork, buildings and limited power works) while most MEP/SCADA/commissioning remains near zero. This is intentionally modest.

## 03_PROGRESS
MONTHLY PROGRESS / REPORTING REGISTER
Assessment convention: monthly reporting. Exact CP-1 billing cut-off / Particular Conditions were not found publicly. 4.19% at 05-May-2026 is public; 12.10% at 31-Aug-2026 is simulated.
Period | Cut-off / Status Date | Cumulative Progress | Basis | Baseline Reference | Note
Oct-2025 | 2025-10-31 |  | Monthly period | Original Contract Baseline Rev 0 | Populate from measured work when actual records exist.
Nov-2025 | 2025-11-30 |  | Monthly period | Original Contract Baseline Rev 0 | Populate from measured work when actual records exist.
Dec-2025 | 2025-12-31 |  | Monthly period | Original Contract Baseline Rev 0 | Populate from measured work when actual records exist.
Jan-2026 | 2026-01-31 |  | Monthly period | Original Contract Baseline Rev 0 | Populate from measured work when actual records exist.
Feb-2026 | 2026-02-28 |  | Monthly period | Original Contract Baseline Rev 0 | Populate from measured work when actual records exist.
Mar-2026 | 2026-03-31 |  | Monthly period | Original Contract Baseline Rev 0 | Populate from measured work when actual records exist.
Apr-2026 | 2026-04-30 |  | Monthly period | Original Contract Baseline Rev 0 | Populate from measured work when actual records exist.
May-2026 | 2026-05-05 | 4.19% | PUBLIC CHECKPOINT | Original Contract Baseline Rev 0 | Public overall project progress checkpoint.
Jun-2026 | 2026-06-30 |  | Monthly period | Original Contract Baseline Rev 0 | Populate from measured work when actual records exist.
Jul-2026 | 2026-07-31 |  | Monthly period | Original Contract Baseline Rev 0 | Populate from measured work when actual records exist.
Aug-2026 | 2026-08-31 | 12.1% | ASSESSMENT | Original Contract Baseline Rev 0 | Current simulated status; not a claimed Kubota record.
BASELINE REVISION RULE
Control State | Revision | Rule
Original Contract Baseline | Rev 0 | Frozen / pristine / never overwritten.
Approved Revised Baseline | Rev n | Create only after formal approval of Variation/EOT/change; retain Rev 0.
Monthly Working Update | Current | Update actuals and remaining forecast each reporting period against the currently approved baseline.

## 04_RECOVERY
THREE-MODEL SCHEDULE CONTROL
Baseline → Actual Progress → Recovery. Data Date: 31-Aug-2026. Native Microsoft Project CPM recalculation governs the forecast; July-2028 remains a separate public target reference.
Model | Data / Anchor Date | Forecast Finish | Δ vs Baseline (wd) | Gain vs Current (wd) | Purpose | Boundary | Native File
1 – Baseline | 2025-10-01 | 2028-02-15 | 0 |  | Preserved assessment CPM reference | Exact start day and detailed logic are assessment conventions | Michael_Futol_Chinaimo_Baseline.mpp
2 – Actual Progress | 2026-08-31 | 2028-06-23 | 111 | 0 | Current status / native CPM forecast | 12.10% status is assessment-simulated; July-2028 is the public target reference, not a forced CPM finish | Michael_Futol_Chinaimo_Actual_Progress.mpp
3 – Recovery | 2026-08-31 | 2028-04-14 | 51 | 60 | Partial recovery from the native current model | 60 wd recovered by native CPM; 51 wd remains vs baseline. Field validation required before commitment | Michael_Futol_Chinaimo_Recovery.mpp
Recovery Action | Assessment Change | Target Gain (wd) | Why | Execution Gate | Key Risk | Owner / Interface | Status
Sedimentation basin workfront | Remaining duration -20 wd | 20 | Sectional fronts / tighter release | Drawings, access, QA hold points | Congestion / rework | Construction + QA/QC | PROPOSED
Rapid sand filter structure | Remaining duration -15 wd | 15 | Earlier interface release | IFC, materials, inspection readiness | Interface clashes | Construction + Engineering | PROPOSED
Internal channels / galleries | Remaining duration -10 wd | 10 | Zone-by-zone handover | Access, waterproofing, inspections | Out-of-sequence work | Construction + QA/QC | PROPOSED
Process piping installation | Remaining duration -10 wd | 10 | Area handover / support readiness | Approved drawings, materials, access | Rework / congestion | M&E + Procurement | PROPOSED
Punch list / rectification | Remaining duration -5 wd | 5 | Progressive punch closure | Turnover dossiers / test packs | Late hidden defects | Commissioning + QA/QC | PROPOSED
Control rule: no recovery duration reduction becomes a commitment until Construction, Engineering, Procurement, QA/QC, HSE and Commercial validate resources, constructability, cost and risk.

## 05_SOURCES
PUBLIC SOURCE BASIS / DATA BOUNDARY
Use public records only for public facts. Anything not supported by those records is labelled assessment simulation.
Date | Source | Public Fact Used | URL
2025-08-20 | Vientiane Times | Package value ¥6,478,257,873; 30-month period; Oct-2025 start; completion in 2028 | https://vientianetimes.org.la/freefreenews/freecontent_159_city_y25.php
2025-08-20 | KPL | Approx. ¥6.48B; construction scheduled Oct-2025; 30 months | https://kpl.gov.la/asean2024/En/detail.aspx?id=94243
2025-08-29 | Kubota | Contract period 30 months; public scope; approx. ¥6B | https://www.kubota.co.jp/news/2025/management-20250829.html
2026-05-05 | Vientiane Times | 4.19% overall progress; key components underway; July-2028 completion target; report says progress in line with planned schedule | https://www.vientianetimes.org.la/freefreenews/freecontent_82_City_y26.php
2026-08-27 | Laotian Times | Broader Vientiane water expansion remains active; no newer Chinaimo-specific progress % stated | https://laotiantimes.com/2026/08/27/vientiane-water-enterprise-reports-usd-4-2-million-profit-103-villages-still-without-water/
| JICA Standard Bidding Documents – Works | JICA requires standard bidding documents for Japanese ODA loan procurement; used here only as framework context, not as proof of CP-1 Particular Conditions. | https://www.jica.go.jp/english/activities/schemes/finance_co/guide/tender/index.html
| JICA payment convention reference | Monthly progress/payment statements are used as an assessment convention; exact CP-1 cut-off and payment Particular Conditions were not found publicly. | https://www.jica.go.jp/english/activities/schemes/finance_co/guide/tender/index.html
BOUNDARY | PUBLIC | ASSESSMENT | DO NOT CLAIM
Progress | 4.19% at 05-May-2026 | 12.10% at 31-Aug-2026 | That 12.10% is a published live figure
Schedule | 30 months; July-2028 current target | Native CPM: 15-Feb-2028 baseline / 23-Jun-2028 current / 14-Apr-2028 recovery; July-2028 remains the public target reference | Contractual EOT entitlement
Commercial | Public package value only | Illustrative BOQ quantities/rates/weights | Kubota BOQ, rates, claims or internal data

## 06_IPC_SAMPLE
SAMPLE INTERIM PAYMENT CERTIFICATE — 31 AUGUST 2026
Assessment sample only. Demonstrates monthly valuation / certification logic; actual CP-1 Contract Data, retention, advance recovery, minimum IPC and tax terms are not publicly available.
Certificate / Statement | IPC-SAMPLE-2026-08 |  | CONTROL NOTE
Reporting Period | 01-Aug-2026 to 31-Aug-2026 |  | Contractor monthly Statement → Engineer's IPC (assessment demonstration)
Status / Cut-off Date | 2026-08-31 |  | Assessment data date
Assessment Control Value (JPY) | 6000000000 |  | Illustrative control budget; not Kubota contract BOQ
Current Cumulative Progress | 12.1% |  | 12.10% simulated status from 02_STATUS
Assumed Previous Certified Progress | 9.5% |  | 9.50% assumed solely to demonstrate current-period certification
Current Period Progress | 2.595% |  | Formula: current cumulative less previous certified
Retention Rate | 10% |  | Illustrative only; actual percentage is Contract Data-dependent
Currency | JPY |  | No FX split simulated
VALUATION | Previous Certified | Current Period | Cumulative | Basis | Assessment Boundary
1. Work executed / earned value | 570000000 | 155700000 | 725700000 | Progress × assessment control value | Illustrative
2. Approved Variations | 0 | 0 | 0 | None included in sample | Actual approved variations would be valued separately
3. Price / legislation adjustment | 0 | 0 | 0 | Not simulated | Contract-dependent
4. Eligible Plant & Materials | 0 | 0 | 0 | Not simulated | Contract-dependent
5. GROSS STATEMENT VALUE | 570000000 | 155700000 | 725700000 | Items 1–4 | Assessment
6. Less: Retention | 57000000 | 15570000 | 72570000 | Illustrative 10% | Actual Contract Data governs
7. Less: Advance payment recovery | 0 | 0 | 0 | Not simulated | Actual contract governs
8. Less: Other deductions / set-offs | 0 | 0 | 0 | Not simulated | Engineer / Contract-dependent
9. NET CERTIFIED / DUE | 513000000 | 140130000 | 653130000 | Gross less deductions | Assessment
AMOUNT OF THIS SAMPLE IPC |  |  | 140130000
SUPPORTING RECORD / CONTROL | Included in this assessment? | What would be used on a live project
Monthly progress report | YES | Measured progress, narrative, photos, programme update and substantiation
Measurement sheets / BOQ backup | YES — assessment BOQ | Signed measurements / approved BOQ rates / quantity records
Approved Variations | NONE IN SAMPLE | Approved variation instructions / valuation records
Materials on Site | NONE IN SAMPLE | Invoices, delivery/storage evidence and eligibility under the Contract
Retention / advance recovery | ASSUMED / ZERO | Exact Contract Data and advance-payment amortisation terms
JICA framework reference: Works GC Sub-Clause 14.3 contemplates a monthly Statement supported by the monthly progress report and includes work executed (including Variations), adjustments, retention, advance-payment movements, eligible Plant/Materials, other additions/deductions and previous certificates. Exact CP-1 Particular Conditions are not claimed here.
Source: https://www.jica.go.jp/activities/schemes/finance_co/procedure/guideline/tender/ku57pq00000v0qfy-att/SBDW_GC.pdf